## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
2OimIvEJRUOT-4cst6YIAwgAACkf | update launch script to take argv | Install / launch scripts | Not started | Medium |  | Dirk Booy | 10/29/2023 |  |  | false | false
AmDrCv_-EkKHzdnh-ewSOQgAFAco | Write up manual tests | Testing scripts | In progress | Medium | Dirk Booy | Dirk Booy | 10/24/2023 |  | 10/26/2023 | false | true
bOPHyPQuxUGpb6j5YZ7CRwgAGRGe | Optional - Pretty up the display terminal printing | Ideas / notes & bugs | Not started | Low |  | Dirk Booy | 10/20/2023 |  |  | false | false |  |  |  |  | Idea! | add logo to splash screen "##########".... "◆ ◆ ◆ " "◆◆ ◆" " ◆◆◆◆ ◆" "◆ ◆ ◆ " "◆◆ ◆◆◆◆ " " " "◆◆◆◆◆◆◆◆" "##########".... make print title stretch to cover the width of the screen
iKTKEsJtYEqUFcm4jNm3swgAE77Y | Screenshot Workplan | Project Management | In progress | Medium | Dirk Booy | Dirk Booy | 10/29/2023 |  | 10/29/2023 | true | false | [5 empty] | Take screenshots of the implementation plan
eVBX8nqxr0WfwcG23EAJOAgAHm3_ | Git Push | Project Management | In progress | Medium | Dirk Booy | Dirk Booy | 10/29/2023 |  | 10/29/2023 | true | false | [5 empty] | Push repo!
Fu6oMTwlgkOFiK-KLPL2lggAB2Tp | Presentation | Presentation | In progress | Low | Dirk Booy | Dirk Booy | 10/16/2023 | 10/26/2023 | 10/28/2023 | false | true |  |  | 0/4 | R10 - explaination of the important parts of code (inc. crucial application logic);R9 Notes - main features and overall structure of app;R10 Slides - Overview of code;R9 Slides - overview of Terminal Application |  | Walk-through of Terminal Application, it's features and how it is used - Slides to contain - Overview Walk-through of the logic of terminal application and code Review of development/build process - challenges, ethical issues, favorite parts, etc
ITj5i7ook0aznAeljnVoMQgACJk3 | README.md | Presentation | Completed | Medium | Dirk Booy | Dirk Booy | 10/16/2023 |  | 10/28/2023 | false | false | 10/29/2023 | Dirk Booy | 2/2 | R2 - Add README Headings;R1 - Complete all the requirements below |  | R1 - Complete all the requirements below R2 - README Headings R3 - References R4 - Link to Source Repository R5 - Code and style Guides R6 - List of features R7 - Implementation plan R8 - Help Documentation (including installation instructions)
0_qbRhVuxkOBUW_ZzG0LPggADp_M | R3 - references section | README | Completed | Medium |  | Dirk Booy | 10/17/2023 |  |  | false | false | 10/29/2023 | Dirk Booy
fcKvzN0Wv0CW3bjjhQ2BAggAEQdA | R1 - Complete all requirements | README | Completed | Medium |  | Dirk Booy | 10/17/2023 |  | 10/28/2023 | false | false | 10/29/2023 | Dirk Booy
dHoCkQXD-kumtKZ69bYAjwgABmgj | R2 - develop & format README.md | README | Completed | Medium |  | Dirk Booy | 10/17/2023 |  | 10/20/2023 | false | false | 10/29/2023 | Dirk Booy
XW5sclLdckaomMr-H0fNqAgAHEtd | R8 - help documentation | README | Completed | Medium |  | Dirk Booy | 10/17/2023 |  | 10/27/2023 | false | false | 10/29/2023 | Dirk Booy | 0/1 | Has installation instructions
OPexvA50bEiMG0EGrfA0kAgAG_T_ | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/29/2023 |  | 10/28/2023 | false | false | 10/29/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
VSgtyB5Z_0a4wxvbNjNB1wgAEHiD | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/29/2023 |  | 10/27/2023 | false | false | 10/29/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
uE8oOqLJ0E2hwK9kQQo4dwgAH7i_ | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/26/2023 |  | 10/26/2023 | false | false | 10/29/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
6tCrxTRxzEihvgqFs-nNZggADjVq | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/29/2023 |  | 10/28/2023 | false | false | 10/29/2023 | Dirk Booy |  |  |  | Push repo!
j20WdYlvY0uHL1qokGi1FAgAHsA3 | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/27/2023 |  | 10/27/2023 | false | false | 10/29/2023 | Dirk Booy |  |  |  | Push repo!
LHldN6Ep50SPydx0pZUqPwgAAbHK | Optional - add question time keeping functionallity | Ideas / notes & bugs | Completed | Low |  | Dirk Booy | 10/19/2023 | 10/17/2023 | 10/28/2023 | false | false | 10/29/2023 | Dirk Booy | 0/2 | limit time to answer question to ~10 seconds;Update score function to give more score the faster the question is answered | Idea!
EXsyqpH9mUagSLF5iqHzkggABDW_ | BUG - Disable input during wait | Ideas / notes & bugs | Completed | Low |  | Dirk Booy | 10/19/2023 |  |  | false | false | 10/29/2023 | Dirk Booy |  |  | Bug | integrate this concept into quiz wait between questions to stop accidental answering before question displayed: https://stackoverflow.com/questions/29289945/how-to-temporarily-disable-keyboard-input-using-python
and79w1KukytO7UQGb979QgACTWi | Optional extra - verbose display results | Quiz Taking Function | Completed | Low |  | Dirk Booy | 10/19/2023 |  | 10/28/2023 | false | false | 10/29/2023 | Dirk Booy |  |  | Idea! | Add review of questions wrong to fun_with_bonus()
TsuGre3Rf0yF3qzcI5wxUAgAAyze | Launch bash script | Install / launch scripts | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/26/2023 | false | false | 10/29/2023 | Dirk Booy |  |  |  | test if python installed Launch in quiz mode (default) or edit mode if edit argv added Check python installed Check pip installed Launch script: Python3 -m venv .venv Source .venv/ bin/activate Pip install requirements.txt Python3 main.py Deactivate chmod (-rw) the quiz_data folder to ensure access
WBLXwH-Mg06UoC-gjdK8UggAGsUT | Data validation on quiz file | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/25/2023 |  |  | false | false | 10/29/2023 | Dirk Booy |  |  |  | Validate questions are formatted correctly, Lists of lists (5 items each) Validate at least 5 questions
3BRy2IBX40mOCMKoZNoDrQgADARO | update main.py help loop | Help Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/29/2023 |  |  | false | false | 10/29/2023 | Dirk Booy
QucZOf3skEWfnnSYjAI6OQgAAqMl | Write help files | Help Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/24/2023 | false | false | 10/29/2023 | Dirk Booy | 0/2 | edit uiz help file;take quiz help
vLTEIRQ-6EGqUlUuvt3SCAgACPEI | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/26/2023 |  | 10/26/2023 | false | false | 10/27/2023 | Dirk Booy |  |  |  | Push repo!
3kyuGEeBt0SYueGHpiwMJggAC82V | Check read only access to quiz_data folder - write to file | Testing scripts | Completed | Medium | Dirk Booy | Dirk Booy | 10/25/2023 |  |  | false | false | 10/27/2023 | Dirk Booy
HppfBh2GQ0OW0_5BtBUocQgAB84o | Delete quiz function | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/25/2023 |  | 10/26/2023 | false | false | 10/26/2023 | Dirk Booy
GMsos5mj90SGjC798p-79ggABHzl | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/26/2023 |  | 10/25/2023 | false | false | 10/26/2023 | Dirk Booy |  |  |  | Push repo!
zF8u1pDu4kCUYtGW4lus7QgABd6A | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/24/2023 |  | 10/25/2023 | false | false | 10/26/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
d6SpowKl702EnzVS0NXPYwgACaEE | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/23/2023 |  | 10/24/2023 | false | false | 10/26/2023 | Dirk Booy |  |  |  | Push repo!
BgV4z10sI0-97XTJUceUGAgABTLM | R6 - Describe Key features >3 | README | Completed | Medium |  | Dirk Booy | 10/17/2023 |  |  | false | false | 10/25/2023 | Dirk Booy
JSvZQdsIREO0wOXflRLVewgAEmDy | R7 - Implementation Plan | README | Completed | Medium |  | Dirk Booy | 10/17/2023 |  | 10/20/2023 | false | false | 10/25/2023 | Dirk Booy
dUfN8M0NgU2oqI7W2Xzi8AgAB6zi | disable using commas in questions / answers writing - will cause errors in csv files | Ideas / notes & bugs | Completed | Medium | Dirk Booy | Dirk Booy | 10/24/2023 |  | 10/25/2023 | false | false | 10/25/2023 | Dirk Booy |  |  | Bug
3-kLJ6jCXkqQiOiKNhalkAgAFXTP | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/24/2023 |  | 10/24/2023 | false | false | 10/24/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
uLCG9ARlcUeT9F4z9YiYMQgACDZo | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/23/2023 |  | 10/23/2023 | false | false | 10/24/2023 | Dirk Booy |  |  |  | Push repo!
vNXEX2sRf0aNKnsVrtATTQgAERD8 | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/23/2023 |  | 10/23/2023 | false | false | 10/24/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
78wG1K5NaEagDad7Xc-PkQgAB4Xm | Create Pytest for Quiz editing feature - write / delete question | Testing scripts | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/26/2023 | false | false | 10/24/2023 | Dirk Booy |  |  |  | This test will: 1. Get the list of quiz topics 2. Write a test question to the first quiz file 3. Load questions from quiz file 4. Confirm test question was written to file 5. Delete test question from file 6. Confirm deletion of test question form file It will test the following functions in file_handling.py: 1. get_topics_from_dir() 2. write_new_question_to_file(topic) 3. get_question_list_from_file(quiz_title) 4. delete_question(topic)
lypehlAALkyOSkTi001KhAgAFJxI | Pytest - write new quiz, read quiz from file | Testing scripts | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/26/2023 | false | false | 10/24/2023 | Dirk Booy |  |  |  | This test will: 1. create a test quiz, 2. write it to a file, 3. check that the newly generated quiz appears in the topics list 4. read the quiz from file back into the program and compare it to the original generated quiz. It will test the following functions in file_handling.py: 1. write_full_quiz_to_file(topic: str, question_list: list): 3. get_topics_from_directory() 2. get_question_list_from_file(quiz_title: str)
q3g0mD6Zx0u6mAzZ2Rv3AggAHevH | Scope Pytest automated testing | Testing scripts | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/25/2023 | false | false | 10/24/2023 | Dirk Booy
GZYOqcgsoUqeVwwoaT2EswgACRYT | Press Enter to Continue | Ideas / notes & bugs | Completed | Medium | Dirk Booy | Dirk Booy | 10/22/2023 |  |  | false | false | 10/24/2023 | Dirk Booy |  |  |  | use getpass.getpass("Press Enter to continue...")
WpqiLe5gJEaDmmRLtim2fggAEy5a | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/23/2023 |  | 10/22/2023 | false | false | 10/23/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
xUqqYr5saU2PrtZi1DxO7wgACG6u | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/23/2023 |  | 10/22/2023 | false | false | 10/23/2023 | Dirk Booy |  |  |  | Push repo!
ydydvEPxZkio_AIMhLwVtggAFsMZ | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/20/2023 |  | 10/21/2023 | false | false | 10/23/2023 | Dirk Booy |  |  |  | Push repo!
qfwFe7HTAECZVb1wOQPa8ggADaoY | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/20/2023 |  | 10/21/2023 | false | false | 10/23/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
K3d0_gBmakSvcsS4kXKzfwgAEnbR | code help loop | Help Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/26/2023 | false | false | 10/22/2023 | Dirk Booy
Kq9ihg6ujU2Dtz0BN82xIQgAEyj9 | Data validation of quiz lists | Edit Quiz functions | Completed | Medium |  | Dirk Booy | 10/20/2023 |  | 10/21/2023 | false | false | 10/22/2023 | Dirk Booy
r4K35wMzKkSApaj9qR5HyAgAEQDf | delete question loop | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/21/2023 | false | false | 10/22/2023 | Dirk Booy |  |  |  | get list of questions print to terminal (numbered) user input number print question get confirmation to delete remove from question list save question list to file
_lVTSmKSykShJJ1wq3gUwwgAGyQ6 | Select Quiz to edit | Initiation & menu navigation | Completed | Medium | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/21/2023 | false | false | 10/22/2023 | Dirk Booy | 3/6 | select New Quiz or edit existing;New quiz - need to add 10 Qs;validate input;get user input - which quiz;edit quiz - get list of quizzes (function);pass selected quiz to edit_quiz function
QdaBbpcvNkiEYAQYUcPfIwgAHnnq | Select quiz function | Initiation & menu navigation | Completed | Important | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/24/2023 | false | false | 10/22/2023 | Dirk Booy |  |  |  | Get available quiz files - stored in JSON format in quiz directory - make a specific naming convention to ensure only quiz files get eg quiz_quiz_title.json - convert file names to the Quiz Title eg quiz_quiz_title.json ==> "Quiz Title" - add to a dict {"Quiz Title" : "filename", ... ] : eg {"Title" :"quiz_quiz_title.json", ...} - add keys to list, sort - print a numbered list of -
kwAA13bJy0WH7-Hy0-T4EwgAEStN | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy |  |  |  | Push repo!
MD31Yq4M50SBXdd6r9PM8QgAGJeB | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
hJIsC_Ieq0mQvDA7TumarAgAB1px | Read quiz questions from file | Initiation & menu navigation | Completed | Urgent | Dirk Booy | Dirk Booy | 10/20/2023 |  |  | false | false | 10/20/2023 | Dirk Booy | 2/3 | Data validation;import code;Create test file to import
oIjAvqZ8bEizcH95Q6LlMAgAAMM_ | read file - import questions form file | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/20/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy
mVdsT_fkH0CPaWAOvcBHpggADiM9 | Read file - list of topics | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/20/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy
qGtPgvfY_06_EgFAyq8KCAgAEbUa | Create New New Quiz function | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/20/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy
-wRkCaP3I0uLnfmAyyq68AgAEznl | Add question | Edit Quiz functions | Completed | Medium | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/21/2023 | false | false | 10/20/2023 | Dirk Booy | 0/6 | confirm with user ;save to file;Get input: Question, correct answer, wrong Answers x3;Add to quiz list ;Format to add to Quiz list;validate inputs
XGU2jtKpT0-8GOOCtDqegggAALe_ | Menu loop | Initiation & menu navigation | Completed | Important | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy | 2/2 | Main menu loop;Print Welcome message |  | Print Welcome message Main Menu loop - Play ¦ Select quiz ¦ call selected quiz - Edit quiz ¦ call edit loop - Help ¦ call help - Credits ¦ call credits - Quit ¦ break main loop (ends program)
0JjU1YUErEaaNWTOgqNnawgADG7N | Quiz round handler function | Quiz Taking Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/20/2023 | false | false | 10/20/2023 | Dirk Booy | 7/7 | Loop over 10 question list;In loop - Call display question function;In Loop -call get input function;mark question - adjust score;call q_list function compile 10 randomly selected questions from list questions in topic; Call fun with bonus function (present score);Add optional extra card - additional feedback - save wrong q&A display at end |  | calls functions for a round of quiziness (handles scoring) - call q_list function compile 10 randomly selected questions from list questions in topic - loop over 10 question list - Call display question function - call get input function - mark question - adjust score - Call fun with bonus function (present score)
ZBCHRWemYkqpTByIUwpSAAgABgaA | display results | Quiz Taking Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/19/2023 | false | false | 10/20/2023 | Dirk Booy
Ke3MBpWajUmwPKDRg0dEAAgAEbW5 | Keep round score functionality | Quiz Taking Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/18/2023 |  | 10/19/2023 | false | false | 10/20/2023 | Dirk Booy
xkY-JOnZeUCdY-vqdMHxfggAGAzn | Get user answer function | Quiz Taking Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 | 10/19/2023 | 10/19/2023 | false | false | 10/19/2023 | Dirk Booy |  |  |  | Get a confirmed valid answer from user Loop until valid answer is provided valid answer will be input().lower() == "a" ¦ "b" ¦ "c" ¦ "d" ¦ "1" ¦ "2" ¦ "3" ¦ "4" consider typing out full answer as acceptable?
ySaafWPkakmIzsttRN5DGwgAEOTf | Git Push | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/19/2023 | false | false | 10/19/2023 | Dirk Booy |  |  |  | Push repo!
34RhLU9Myk-12ReZq1X-XwgAD9FX | display question function | Quiz Taking Function | Completed | Medium | Dirk Booy | Dirk Booy | 10/16/2023 |  | 10/19/2023 | false | false | 10/19/2023 | Dirk Booy |  |  |  | develop a function to display question and answers
74aINq-WsE60DRs5GrupPAgAArCo | Get 10q from q list | Quiz Taking Function | Completed | Important | Dirk Booy | Dirk Booy | 10/17/2023 | 10/19/2023 | 10/19/2023 | false | false | 10/19/2023 | Dirk Booy |  |  |  | Build function randomly select 10 questions from a large list of questions
3LzxLnmHw0-6TxVjyKzvAQgADUom | Implementation Plan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/19/2023 | false | false | 10/19/2023 | Dirk Booy | 3/3 | Set tasks to complete features;Assign Due date for tasks;Outline Application Features (README.md) |  | Outline Application Features
GO76kmvXckebYZdIBxbQewgABGJL | Screenshot Workplan | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/19/2023 |  | 10/19/2023 | false | false | 10/19/2023 | Dirk Booy |  |  |  | Take screenshots of the implementation plan
2BVNKiZ6aEa5sBDvQXLTFQgAHXMQ | R5 - Identify Style guide | README | Completed | Medium | Dirk Booy | Dirk Booy | 10/17/2023 |  |  | false | false | 10/19/2023 | Dirk Booy
9C0gM6PylkqQC5LfpZY7ZAgACDho | R4 - link to your source control repository | README | Completed | Medium | Dirk Booy | Dirk Booy | 10/17/2023 |  |  | false | false | 10/19/2023 | Dirk Booy
Zo5-fePzCUybSX25xoh5bggAHJ7W | App Idea approval | Project Management | Completed | Medium | Dirk Booy | Dirk Booy | 10/16/2023 |  | 10/20/2023 | false | false | 10/19/2023 | Dirk Booy

## Plan name
Plan name | Dirk Booy - T1A3
Plan ID | MN5oAS6OQkuomEOswzAJbQgAGgfe
Date of export | 10/29/2023